VLUMEAWARE

Compliance Roadmap & Requirements Checklist

SOC 2  ·  ISO/IEC 27001:2022  ·  ISO/IEC 42001:2023

Prepared for Vlumetech LTD

Working document — for team prioritisation

Version 1.0  ·  30 September 2026

1.  Executive summary

This document lists what Vlumetech must do to achieve three independent compliance goals for the Vlumeaware platform, and turns each into a prioritised, ownable checklist so the team can plan the work. All three are earned through an external assessor — none can be self-declared.

What each standard is

SOC 2 is an attestation, not a certification. A licensed CPA firm examines your controls against the AICPA Trust Services Criteria and issues a report. Type I tests design at a point in time; Type II tests that controls operated effectively over a period (typically 6–12 months). Customers almost always want Type II.

ISO/IEC 27001:2022 is a certification of an Information Security Management System (ISMS). An accredited certification body audits in two stages; the certificate lasts three years with annual surveillance audits. The core is management-system clauses 4–10 plus the 93 Annex A controls.

ISO/IEC 42001:2023 is a certification of an Artificial Intelligence Management System (AIMS) — the first management-system standard for AI. It applies to Vlumeaware because the product uses large language models to generate phishing lures and training narratives, which is an AI use with real safety, dual-use and data-governance considerations. Structure mirrors 27001: clauses 4–10 plus AI-specific Annex A controls.

The efficient path: build once, certify many

Roughly 60–70% of the effort is shared. A single ISMS backbone — policies, a risk assessment, asset and access management, HR security, supplier management, incident response, business continuity, logging and monitoring, change management, internal audit and management review — satisfies the bulk of all three standards at once. Section 2 covers this shared foundation; Sections 3–5 cover each standard's specific additions; Section 6 maps the overlap; Section 7 gives a phased plan.

Where Vlumeaware stands today

The technical access-control and audit work completed to date (multi-factor authentication, role-based access with a generated authorization matrix, query-layer tenant isolation, authentication and privileged-access audit logging, rate limiting and account lockout) is a genuine head-start on the logical-access and operations controls. But most of a compliance programme is organisational policy and evidence-over-time, which has not yet started. Honest current status: strengthening controls — not yet audit-ready, and not compliant.

Legend used throughout:  Done = in place & evidenced  ·  Partial = partially in place  ·  Not started = to do.   Priority:  P1 = foundational / do first  ·  P2 = required, second wave  ·  P3 = later / maturity.

2.  Shared foundation (satisfies SOC 2 + ISO 27001 + ISO 42001)

Do these first: each item is required by all three standards (or two of the three) and is mostly organisational rather than code. This is the ISMS/AIMS backbone.

2.1  Programme setup & governance

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| F1 | Appoint an ISMS/compliance owner and an executive sponsor (management commitment) | Not started | P1 | CEO/CTO |
| F2 | Define scope & system boundary (Vlumeaware product, environments, data, people, third parties) | Not started | P1 | CTO |
| F3 | Choose framework tooling / GRC platform (e.g. Vanta, Drata, Secureframe) to automate evidence | Not started | P1 | CTO |
| F4 | Select assessors: SOC 2 CPA firm; ISO 27001 & 42001 accredited certification body | Not started | P2 | CEO |
| F5 | Establish a security steering group and a recurring management-review meeting | Not started | P2 | CTO |

2.2  Policies (the core policy set)

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| F6 | Information Security Policy (top-level, management-approved) | Not started | P1 | Compliance |
| F7 | Acceptable Use, Access Control, and Password/Authentication policies | Not started | P1 | Compliance |
| F8 | Data Classification, Retention & Disposal policy | Not started | P1 | Compliance |
| F9 | Risk Management policy & methodology | Not started | P1 | Compliance |
| F10 | Incident Response policy & plan (with roles, severities, timelines) | Not started | P1 | CTO |
| F11 | Business Continuity & Disaster Recovery policy + plan | Not started | P2 | CTO |
| F12 | Change Management policy (SDLC, code review, approvals, release) | Partial | P2 | CTO |
| F13 | Vendor / Third-party (supplier) management policy | Not started | P2 | Compliance |
| F14 | HR security policy (screening, onboarding, offboarding, disciplinary) | Not started | P2 | HR |
| F15 | Cryptography / key-management policy | Not started | P2 | CTO |
| F16 | Secure development policy & guidelines | Partial | P2 | CTO |

2.3  Risk & asset management

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| F17 | Asset inventory (systems, data stores, endpoints, SaaS, repositories, domains) | Not started | P1 | CTO |
| F18 | Data map / data flow diagram incl. personal data and AI training/inference data | Not started | P1 | CTO |
| F19 | Risk assessment: identify, analyse, evaluate risks against the scope | Not started | P1 | Compliance |
| F20 | Risk treatment plan (accept / mitigate / transfer / avoid) with owners & dates | Not started | P1 | Compliance |
| F21 | Vendor risk register & due-diligence (Supabase, Render, Vercel, Resend, AI providers) | Not started | P2 | Compliance |

2.4  People & operations

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| F22 | Background checks / screening for staff with production access | Not started | P2 | HR |
| F23 | Security-awareness training for all staff (and evidence of completion) | Not started | P1 | HR |
| F24 | Onboarding & offboarding checklists (access grant/revoke within SLA) | Not started | P1 | HR/CTO |
| F25 | Quarterly user access reviews (who has access to what, least privilege) | Not started | P1 | CTO |
| F26 | Centralised logging & monitoring with alerting on security events | Partial | P1 | CTO |
| F27 | Vulnerability management: dependency scanning, patching cadence | Not started | P1 | CTO |
| F28 | Annual penetration test by an external firm | Not started | P2 | CTO |
| F29 | Backup & restore procedure, with periodic restore tests | Partial | P2 | CTO |
| F30 | Internal audit of the management system before the external audit | Not started | P2 | Compliance |

3.  SOC 2 — specifics

SOC 2 is organised around the Trust Services Criteria. Security (the Common Criteria, CC1–CC9) is mandatory; add Availability and Confidentiality (both highly relevant to a SaaS handling client employee data), and consider Privacy. Below are the SOC-2-specific tasks beyond the shared foundation in Section 2.

3.1  Common Criteria coverage (CC1–CC9)

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| S1 | CC1 Control Environment: org chart, roles, code of conduct, board/mgmt oversight | Not started | P2 | CEO |
| S2 | CC2 Communication & Information: security commitments published to staff & customers | Not started | P2 | Compliance |
| S3 | CC3 Risk Assessment: formal, documented, refreshed at least annually (see F19) | Not started | P1 | Compliance |
| S4 | CC4 Monitoring: continuous control monitoring + periodic evaluations | Partial | P2 | CTO |
| S5 | CC5 Control Activities: controls mapped to risks, documented | Not started | P2 | Compliance |
| S6 | CC6 Logical & Physical Access: MFA, RBAC, provisioning, encryption, tenant isolation | Partial | P1 | CTO |
| S7 | CC7 System Operations: monitoring, incident detection & response, change tracking | Partial | P1 | CTO |
| S8 | CC8 Change Management: SDLC controls, approvals, testing, rollback | Partial | P2 | CTO |
| S9 | CC9 Risk Mitigation: vendor risk, business disruption, insurance | Not started | P2 | Compliance |

3.2  SOC 2 process tasks

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| S10 | Decide category scope (Security + Availability + Confidentiality recommended) | Not started | P1 | CTO |
| S11 | Draft the System Description (the narrative the SOC 2 report is built on) | Not started | P2 | Compliance |
| S12 | Readiness assessment / gap analysis with the CPA firm | Not started | P2 | Compliance |
| S13 | Type I audit (design of controls at a point in time) | Not started | P2 | External |
| S14 | Operate controls & collect evidence over the observation window (6–12 months) | Not started | P3 | All |
| S15 | Type II audit & report issuance; plan annual renewal | Not started | P3 | External |

4.  ISO/IEC 27001:2022 — specifics

27001 certifies a management system. Clauses 4–10 are mandatory and largely covered by Section 2. The differentiators are the Statement of Applicability against the 93 Annex A controls, the risk-treatment linkage, and the two-stage certification audit.

4.1  Mandatory ISMS clauses (4–10)

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| I1 | Clause 4 Context: interested parties, ISMS scope statement | Not started | P1 | Compliance |
| I2 | Clause 5 Leadership: policy, roles & responsibilities, management commitment | Not started | P1 | CEO |
| I3 | Clause 6 Planning: risk assessment & treatment, ISMS objectives | Not started | P1 | Compliance |
| I4 | Clause 6 Statement of Applicability (SoA): justify inclusion/exclusion of all 93 controls | Not started | P1 | Compliance |
| I5 | Clause 7 Support: resources, competence, awareness, documented information control | Not started | P2 | Compliance |
| I6 | Clause 8 Operation: execute the risk treatment plan | Not started | P2 | CTO |
| I7 | Clause 9 Performance evaluation: metrics, internal audit, management review | Not started | P2 | Compliance |
| I8 | Clause 10 Improvement: nonconformities, corrective actions, continual improvement | Not started | P3 | Compliance |

4.2  Annex A control themes (93 controls) — areas needing attention

Most Annex A controls are addressed by Section 2 policies plus existing technical controls. The themes and the notable gaps for Vlumeaware:

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| I9 | A.5 Organizational (37): policies, roles, supplier & cloud security, threat intel, incident mgmt | Partial | P2 | Compliance |
| I10 | A.6 People (8): screening, terms, awareness, disciplinary, remote working | Not started | P2 | HR |
| I11 | A.7 Physical (14): mostly inherited from cloud providers; document responsibility split | Partial | P3 | CTO |
| I12 | A.8 Technological (34): access control, crypto, logging, secure dev, change, backup, DLP | Partial | P1 | CTO |
| I13 | Gap: cryptography & key management formalised (A.8.24) + secrets rotation | Not started | P1 | CTO |
| I14 | Gap: secure development lifecycle evidence (A.8.25–A.8.31) — reviews, testing, separation | Partial | P2 | CTO |
| I15 | Gap: logging monitored & protected from tampering (A.8.15–A.8.16) | Partial | P1 | CTO |

4.3  Certification process

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| I16 | Run the ISMS for a minimum period (~3 months of records) before Stage 2 | Not started | P2 | Compliance |
| I17 | Internal audit + management review completed (mandatory before certification) | Not started | P2 | Compliance |
| I18 | Stage 1 audit (documentation review) by accredited body | Not started | P2 | External |
| I19 | Stage 2 audit (implementation & effectiveness); close any nonconformities | Not started | P3 | External |
| I20 | Certificate issued (3-year cycle); annual surveillance audits | Not started | P3 | External |

5.  ISO/IEC 42001:2023 — AI Management System specifics

42001 applies because Vlumeaware uses LLMs (currently DeepSeek / Anthropic) to generate phishing simulation content and training narratives. This is an AI use with genuine dual-use, safety and data-governance dimensions — precisely what 42001 governs. It reuses the management-system backbone from Section 2; the AI-specific additions are below.

5.1  AIMS clauses & AI governance

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| A1 | Define AI policy and the organisation's role (provider vs deployer of AI) | Not started | P1 | CTO |
| A2 | AI system inventory: which features use AI, which models/providers, for what purpose | Not started | P1 | CTO |
| A3 | AI risk assessment (distinct from security risk): misuse, bias, harmful output, hallucination | Not started | P1 | CTO |
| A4 | AI system impact assessment (AIA): effects on individuals & society, incl. dual-use of phishing content | Not started | P1 | CTO |
| A5 | Define AIMS objectives and acceptable-use boundaries for generated content | Not started | P2 | CTO |

5.2  AI Annex A controls (the AI-specific work)

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| A6 | Data governance for AI: sources, quality, and handling of any data sent to model providers | Not started | P1 | CTO |
| A7 | Human oversight: review/guardrails on AI-generated lures & narratives before use | Partial | P1 | CTO |
| A8 | Transparency: disclose to customers where/how AI is used in the product | Not started | P2 | Compliance |
| A9 | AI lifecycle management: model selection, change control, evaluation, monitoring for drift | Not started | P2 | CTO |
| A10 | Third-party AI governance: DPAs & terms with model providers; data-retention & training-use review | Not started | P1 | Compliance |
| A11 | Guardrails against misuse of generated phishing content (abuse, safety controls, logging) | Partial | P1 | CTO |
| A12 | Incident handling for AI-specific failures (harmful/unsafe output) added to IR plan | Not started | P2 | CTO |

5.3  Certification process

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| A13 | Internal audit + management review of the AIMS | Not started | P2 | Compliance |
| A14 | Stage 1 & Stage 2 certification audit (can share the body/timing with 27001) | Not started | P3 | External |
| A15 | Certificate issued (3-year cycle) + annual surveillance | Not started | P3 | External |

6.  Cross-framework overlap

What one activity buys across the three standards — plan the shared items once.

| Activity / control area | SOC 2 | ISO 27001 | ISO 42001 |
| --- | --- | --- | --- |
| Security policies & governance | Yes | Yes | Yes |
| Risk assessment & treatment | Yes | Yes | Yes (+AI risk) |
| Access control, MFA, tenant isolation | Yes | Yes | Yes |
| Logging, monitoring & incident response | Yes | Yes | Yes (+AI incidents) |
| HR security & awareness training | Yes | Yes | Yes |
| Vendor / third-party management | Yes | Yes | Yes (+model providers) |
| Change management & secure SDLC | Yes | Yes | Yes |
| Business continuity & backups | Yes | Yes | Partial |
| Statement of Applicability | No | Yes | Yes |
| AI risk, impact assessment & oversight | No | No | Yes |
| External audit / attestation required | Yes (CPA) | Yes (cert body) | Yes (cert body) |

7.  Suggested phased roadmap

Phase 0 — Foundation (months 0–2)

Appoint owner + sponsor; define scope; select GRC tooling (F1–F5).

Rotate the exposed Supabase credentials immediately (open security item).

Draft the core policy set and stand up the risk assessment & asset inventory (F6–F20).

Phase 1 — Implement controls (months 2–5)

Close technical P1s: audit tamper-evidence, full export/access logging, Postgres RLS backstop, secrets/key management, vulnerability scanning (F26–F27, I13–I15).

Roll out awareness training, onboarding/offboarding, access reviews (F22–F25).

Write the SoA and run the AI risk & impact assessments (I4, A3–A4).

Phase 2 — Assess (months 4–7)

SOC 2 readiness assessment → Type I; ISO 27001/42001 internal audit → Stage 1.

Book an external penetration test (F28).

Phase 3 — Certify & sustain (months 6–15)

ISO 27001 & 42001 Stage 2 audits and certification; SOC 2 Type II observation window then report.

Establish surveillance/renewal cadence and continual improvement.

Indicative only; timelines depend on team capacity and assessor scheduling. SOC 2 Type II is gated by its observation window, so it finishes last.

8.  Vlumeaware technical state & open items

Already in place (evidence for CC6/CC7 and Annex A.8):

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| T1 | Multi-factor authentication (TOTP), enforced for staff | Done | — | CTO |
| T2 | Role-based access control + generated authorization matrix | Done | — | CTO |
| T3 | Query-layer multi-tenant isolation (fail-closed, regression-guarded) | Done | — | CTO |
| T4 | Authentication & privileged-access audit logging | Done | — | CTO |
| T5 | Rate limiting & account lockout | Done | — | CTO |
| T6 | TLS in transit; encryption at rest via managed providers | Partial | P2 | CTO |

Open technical items (carry into Phase 1):

| ID | Task | Status | Priority | Owner |
| --- | --- | --- | --- | --- |
| T7 | Rotate exposed Supabase DB password (known leaked credential) | Not started | P1 | CTO |
| T8 | Audit log tamper-evidence (hash chain / WORM storage) | Not started | P1 | CTO |
| T9 | Finish data-export/access audit coverage (risk CSV, cert PDF, credential views) | Partial | P1 | CTO |
| T10 | Postgres Row-Level Security as a data-tier isolation backstop | Not started | P1 | CTO |
| T11 | Define & enforce audit-log retention (recommend 13 months) | Not started | P2 | CTO |
| T12 | Dependency/vulnerability scanning in CI + patch cadence | Not started | P1 | CTO |

This is a working document. As items are completed, update Status and attach evidence in the GRC tool. None of the three standards is achieved until an external assessor has examined the operating controls.